RWANDA MUSLIM COMMUNITY

Digital Platform

Implementation Plan

Project Manager Deliverable

Step-by-Step Phased Implementation Guide

Version 1.0  |  June 2026  |  Confidential

| Document Attribute | Detail |
| --- | --- |
| Project Name | Rwanda Muslim Community (RMC) Digital Platform |
| Document | Implementation Plan — Phased Approach |
| Prepared By | Project Management Office |
| Version | 1.0 |
| Date | June 2026 |
| Status | Approved for Execution |
| Methodology | Agile / Scrum with Fixed-Phase Gates |
| Technology Stack | NestJS · Next.js · PostgreSQL · AWS · Docker |
| Total Phases | 8 Implementation Phases |
| Estimated Duration | 34 Weeks (approx. 8.5 months) |

# EXECUTIVE SUMMARY

This document defines the complete, step-by-step implementation plan for the Rwanda Muslim Community (RMC) Digital Platform — a comprehensive digital ecosystem serving members, mosque administrators, donors, students, and the public across Rwanda and the diaspora.

The platform covers 14 functional domains including public web services, member management, mosque management, donation and financial management, events, communications, AI assistant, mobile PWA, and multilingual support (Kinyarwanda, English, Arabic).

The implementation is organized into 8 structured phases, each with defined objectives, deliverables, teams, timelines, and quality gates. Each phase builds upon the previous, ensuring a stable foundation before adding complexity.

## Implementation Philosophy

- Foundation First — infrastructure, security, and core data models are built before features

- Incremental Delivery — working software is delivered at the end of every 2-week sprint

- Quality Gates — no phase advances without passing defined acceptance criteria

- Risk-Driven Sequencing — highest-risk integrations (payments, AI) are tackled early

- Stakeholder Visibility — weekly status reports; demo at end of every phase

- Documentation as Code — all decisions, APIs, and architecture documented in parallel with development

## Phase Summary

| Phase | Title | Duration | Key Output |
| --- | --- | --- | --- |
| 1 | Environment & Foundation Setup | Weeks 1–3 | AWS infra, CI/CD, DB schema, auth system live |
| 2 | Core Platform & Member Management | Weeks 4–8 | Members, mosques, public website live |
| 3 | Services & Payment Integration | Weeks 9–14 | All services, MoMo/BK/Visa payments live |
| 4 | Donation & Financial Management | Weeks 15–18 | Campaigns, Zakat, financial reports live |
| 5 | Events, Communication & Notifications | Weeks 19–21 | Events, SMS, email, push notifications live |
| 6 | Analytics, Reports & AI Assistant | Weeks 22–26 | Dashboards, AI chatbot, knowledge base live |
| 7 | Mobile PWA, Schools & Optimization | Weeks 27–30 | PWA, Play Store, Schools module live |
| 8 | Testing, Security Audit & Launch | Weeks 31–34 | Full QA, pen test, UAT, go-live, training |

# HOW TO READ THIS PLAN

Each phase is presented with a consistent structure to ensure clarity for all team members:

| Section | Content |
| --- | --- |
| Phase Overview | Goal, duration, and strategic context for the phase |
| Objectives | Specific, measurable outcomes the team must achieve |
| Team Involved | Roles actively contributing during this phase |
| Pre-conditions | What must be true / complete before phase can start |
| Sprint Breakdown | 2-week sprint goals, stories, and acceptance criteria |
| Deliverables | Concrete outputs (code, documents, deployed systems) |
| Quality Gate | Pass/fail criteria before the phase is considered complete |
| Risks & Mitigations | Phase-specific risks and how the PM will handle them |
| Stakeholder Touchpoints | Meetings, demos, approvals, and communications |

## Definition of Done (Global)

Every user story and feature must satisfy ALL of the following before it is counted as "Done":

- Code is written, peer-reviewed (PR approved by at least 1 senior developer), and merged to the develop branch

- Unit tests written and passing; code coverage ≥ 80% for the module

- Integration tests pass on the CI pipeline

- Feature tested on mobile (375px) and desktop (1440px)

- Multilingual tested: Kinyarwanda, English, Arabic (RTL where applicable)

- API endpoint documented in OpenAPI/Swagger

- No critical or high security vulnerabilities introduced (Trivy + npm audit)

- Deployed and verified on staging environment

- Product Owner / Business Analyst sign-off obtained

## Roles & Responsibilities

| Role | Count | Core Responsibilities |
| --- | --- | --- |
| Project Manager (PM) | 1 | Plan, track, communicate, unblock, risk management, stakeholder reporting |
| Tech Lead / Architect | 1 | Architecture decisions, code standards, PR reviews, technical guidance |
| Backend Developer (NestJS) | 2 | API development, integrations, background jobs, database queries |
| Frontend Developer (Next.js) | 2 | Public website, admin dashboard, member portal, PWA |
| Database Engineer | 1 | Schema design, migrations, performance tuning, backups |
| DevOps Engineer | 1 | AWS infrastructure, Docker, CI/CD pipelines, monitoring |
| QA Engineer | 1 | Test strategy, automated tests, UAT coordination, regression |
| UI/UX Designer | 1 | Wireframes, design system, user testing, accessibility review |
| Business Analyst (BA) | 1 | Requirements, UAT scripts, stakeholder liaison, acceptance sign-off |
| Security Consultant | 1 (part-time, Phase 8) | Penetration testing, security audit, compliance review |

| P1 | Environment & Foundation Setup |
| --- | --- |

| Attribute | Detail |
| --- | --- |
| Duration | Weeks 1 – 3 (6 working days per week, 3 sprints × 2 weeks but compressed) |
| Theme | Infrastructure, tooling, security foundation, and core data architecture |
| Goal | Have a fully operational development environment, CI/CD pipeline, deployed staging and production environments, and a working authentication system with role-based access control |
| Exit Milestone | Developer can register, log in, and receive a JWT; CI/CD deploys automatically to staging on every merge to develop |

## 1.1  Objectives

- Provision and configure all AWS infrastructure (EC2, RDS, S3, VPC, Security Groups, Route 53, ACM)

- Set up Docker-based local development environment with docker-compose

- Create Git repository structure, branching strategy (GitFlow), and branch protection rules

- Build CI/CD pipeline: lint → test → build → scan → deploy to staging → deploy to production (manual gate)

- Design and implement the complete PostgreSQL database schema (all tables, indexes, partitions)

- Implement authentication system: registration, login, JWT (15 min), refresh tokens (7 days), MFA (TOTP), password reset

- Implement role-based access control: SuperAdmin, Admin, Operator, User

- Configure monitoring: Prometheus, Grafana, Loki, Sentry — all dashboards operational

- Deploy Next.js placeholder frontend with health-check page to confirm deployment pipeline works

## 1.2  Team Involved

| Role | Phase 1 Focus |
| --- | --- |
| Tech Lead | AWS architecture review, DB schema design, auth module review, standards setup |
| DevOps Engineer | AWS provisioning, Docker setup, CI/CD pipeline construction, monitoring stack |
| Database Engineer | PostgreSQL schema, migration scripts, index strategy, backup configuration |
| Backend Developer (×2) | Auth module (NestJS): register, login, JWT, MFA, RBAC guards, unit tests |
| Frontend Developer (1 of 2) | Next.js project scaffold, Tailwind config, multilingual setup (i18n), placeholder pages |
| Project Manager | Kick-off meeting, JIRA setup, sprint planning, stakeholder communication plan |
| Business Analyst | Finalize requirement sign-off; prepare acceptance criteria for auth stories |

## 1.3  Pre-Conditions

- RMC has approved the technical stack (NestJS, Next.js, PostgreSQL, AWS)

- Domain name (e.g. rmc.org.rw) is registered and DNS management access is granted to DevOps

- AWS account is created; DevOps has programmatic access (IAM keys)

- Source code repository (GitHub/GitLab) is created; team members have access

- JIRA (or equivalent project board) is set up with all epics and stories imported

- All team members have signed NDAs and are onboarded

## 1.4  Sprint Breakdown

### Sprint 1 — Week 1–2: Infrastructure & DevOps Foundation

| Story | Description | Owner | Acceptance Criteria |
| --- | --- | --- | --- |
| INFRA-001 | Provision AWS VPC with public and private subnets, internet gateway, NAT gateway | DevOps | VPC created; EC2 in private subnet cannot be reached from internet directly |
| INFRA-002 | Launch EC2 instances: App server (t3.large), DB server (t3.medium), Redis (t3.small) | DevOps | All instances running; SSH accessible only from DevOps IP via key pair |
| INFRA-003 | Install and configure PostgreSQL 16 on DB server; create rmc_db database and users | DB Engineer | DB accessible from app server; superuser and app user created; connection tested |
| INFRA-004 | Install Redis 7 on Redis server with AUTH password and maxmemory policy set | DevOps | Redis PING returns PONG from app server; AUTH required; memory policy allkeys-lru |
| INFRA-005 | Configure Nginx as reverse proxy on app server; SSL via AWS ACM/Certbot | DevOps | https://rmc.org.rw returns 200; HTTP redirects to HTTPS; HSTS header present |
| INFRA-006 | Create GitHub repository; configure GitFlow branches (main, develop, feature/*) | Tech Lead | Branches exist; branch protection rules set; PR template created |
| INFRA-007 | Build CI/CD pipeline (GitHub Actions): lint, test, build, security scan, deploy to staging | DevOps | Push to develop triggers pipeline; staging auto-deploys on success |
| INFRA-008 | Set up Docker Compose for local dev: backend, frontend, postgres, redis, mailhog | DevOps | docker compose up starts entire stack; any dev can run locally in < 10 min |
| INFRA-009 | Deploy monitoring stack: Prometheus + Grafana + Loki + Promtail | DevOps | Grafana dashboard shows CPU, memory, HTTP metrics; Loki shows app logs |
| INFRA-010 | Configure AWS S3 bucket: versioning, lifecycle, block public access | DevOps | Bucket created; public access blocked; presigned URL upload tested |

### Sprint 2 — Week 3: Database Schema & Auth System

| Story | Description | Owner | Acceptance Criteria |
| --- | --- | --- | --- |
| DB-001 | Design and implement complete PostgreSQL schema (all Phase 1–8 tables) | DB Eng + Tech Lead | All tables created via TypeORM migrations; FK constraints enforced; indexes applied |
| DB-002 | Set up automated daily DB backup to S3; test restore procedure | DevOps | Backup script runs at 02:00; restore tested and documented; alert on failure |
| AUTH-001 | Member registration endpoint: validate inputs, hash password, create user record | Backend Dev | POST /api/v1/auth/register → 201 with userId; duplicate email/phone → 409 |
| AUTH-002 | Login endpoint: validate credentials, issue JWT (15 min) + refresh token (7 days) | Backend Dev | POST /api/v1/auth/login → 200 with tokens; wrong password → 401 |
| AUTH-003 | Refresh token endpoint: validate refresh, issue new access token, rotate refresh | Backend Dev | POST /api/v1/auth/refresh → 200 new access token; used token rejected |
| AUTH-004 | Logout endpoint: blacklist refresh token in Redis | Backend Dev | POST /api/v1/auth/logout → 200; subsequent refresh with same token → 401 |
| AUTH-005 | Phone OTP verification: generate OTP, send via SMS placeholder, verify | Backend Dev | POST /api/v1/auth/verify-phone with correct OTP → 200; wrong OTP → 400 |
| AUTH-006 | Password reset: forgot-password generates token, reset-password validates and updates | Backend Dev | Full flow tested; reset link expires in 15 min; old password invalid after reset |
| AUTH-007 | TOTP MFA setup and verification (speakeasy library) | Backend Dev | Admin can setup MFA; TOTP code accepted within 30-second window |
| RBAC-001 | Implement RBAC guards: @Roles() decorator, JwtAuthGuard, RolesGuard on all routes | Tech Lead | Operator cannot access Admin endpoints → 403; SuperAdmin can access all → 200 |
| FE-001 | Next.js project: Tailwind CSS, i18n (next-intl), Arabic RTL, font loading | Frontend Dev | Language toggle switches to Kinyarwanda/English/Arabic; RTL applied in Arabic mode |

## 1.5  Deliverables

| # | Deliverable | Format | Owner |
| --- | --- | --- | --- |
| 1 | Fully provisioned AWS environment (VPC, EC2, RDS, S3, Redis) | Live AWS console | DevOps |
| 2 | CI/CD pipeline operational (GitHub Actions) | YAML config in repo | DevOps |
| 3 | Docker Compose local development environment | docker-compose.yml | DevOps |
| 4 | PostgreSQL complete schema (all tables, migrations) | SQL migration files | DB Engineer |
| 5 | Authentication API (register, login, MFA, RBAC) — deployed to staging | NestJS module | Backend Dev |
| 6 | Next.js app scaffold with multilingual support deployed to staging | Next.js project | Frontend Dev |
| 7 | Monitoring dashboards (Grafana) operational | Live dashboards | DevOps |
| 8 | Architecture Decision Record (ADR) document | Markdown in repo | Tech Lead |
| 9 | Sprint 1 & 2 Retrospective reports | JIRA/Confluence | PM |

## 1.6  Quality Gate — Phase 1 Exit Criteria

| Check | Pass Condition |
| --- | --- |
| Infrastructure Health | All EC2, RDS, Redis instances healthy; no alarms in CloudWatch |
| CI/CD Pipeline | Push to develop branch automatically deploys to staging within 10 minutes |
| Authentication | All 8 auth endpoints pass integration tests; 0 test failures |
| RBAC | Role hierarchy enforced on all test endpoints; unauthorized access returns 403 |
| Security Scan | npm audit: 0 critical vulnerabilities; Trivy: 0 critical CVEs in Docker image |
| Database | All migrations apply cleanly; rollback tested; backup/restore verified |
| Monitoring | Grafana shows live metrics; Loki ingesting logs; Sentry connected |
| Team Access | Every developer can run docker compose up and access localhost in < 10 min |

## 1.7  Risks & Mitigations

| Risk | Probability | Mitigation |
| --- | --- | --- |
| AWS account limits blocking provisioning | Low | Request limit increases on day 1; use default region (af-south-1 or eu-west-1) |
| Domain DNS propagation delays | Medium | Start DNS setup in Week 1; use staging subdomain (staging.rmc.org.rw) while waiting |
| DB schema requires major revision after Phase 2 | Medium | Involve BA and Tech Lead in schema review on Day 1; treat schema as living document with migrations |
| MFA library incompatibility | Low | Use battle-tested speakeasy library; test on iOS and Android authenticator apps early |

| P2 | Core Platform & Member Management |
| --- | --- |

| Attribute | Detail |
| --- | --- |
| Duration | Weeks 4 – 8 (5 weeks, 2–3 sprints) |
| Theme | Public-facing website, member lifecycle management, mosque & branch hierarchy |
| Goal | Community members can register online; admins can manage members; the public website is fully live with prayer times, events, announcements, and the homepage — all in 3 languages |
| Exit Milestone | First real community members registered and approved; mosque administrator can log in and view their branch members |

## 2.1  Objectives

- Launch the full public-facing website: homepage (Verse of Day, carousel, prayer times, statistics, events, partners, social feed, footer), About, Services overview, Blog, Gallery, Contact/Mosque finder

- Implement complete member registration and approval workflow (self-register → admin review → approve/reject → notification)

- Build member profiles with photo upload, categorization (Standard, Student, Scholar, Partner, VIP), and digital ID card (PDF with QR code)

- Implement member list views: by area, by mosque, by school, by category, by partner — with export to Excel/PDF

- Build mosque and branch management: mosque CRUD, branch hierarchy, imam assignment, GPS location, contact management

- Implement area management: province, district, sector mapping for member geo-distribution

- Build prayer times engine: calculation by coordinates (Muslim World League method), mosque-specific minute adjustments, public API

- Implement blog with categories, tags, rich text editor, SEO metadata, and comment moderation

- Build gallery module (photos and videos) with category filter

## 2.2  Sprint Breakdown

### Sprint 3 — Weeks 4–5: Public Website

| Story | Description | Owner | Priority |
| --- | --- | --- | --- |
| PW-001 | Homepage: Verse of Day (Arabic + translation, daily rotation) | Frontend + Backend | High |
| PW-002 | Homepage: Welcome carousel (scholarship, programs, donation CTA, announcements) | Frontend | High |
| PW-003 | Homepage: Prayer times widget — geolocation-based, all 5 prayers, countdown | Frontend + Backend | High |
| PW-004 | Homepage: RMC Statistics animated counters (members, mosques, donations, beneficiaries) | Frontend | High |
| PW-005 | Homepage: Upcoming events section (next 5 events with card layout) | Frontend + Backend | High |
| PW-006 | Homepage: Announcements ticker and cards | Frontend + Backend | High |
| PW-007 | Homepage: Partners logo grid | Frontend | Medium |
| PW-008 | Homepage: Social media feed (Facebook/Instagram embed) | Frontend | Medium |
| PW-009 | About Us page: leadership, mission, vision, history, areas of intervention | Frontend | High |
| PW-010 | Services overview page: all 7 services with descriptions and CTA buttons | Frontend | High |
| PW-011 | Contact page: Find nearest mosque (map), contact form, social links | Frontend + Backend | High |
| PW-012 | Language switcher: Kinyarwanda/English/Arabic; RTL layout for Arabic | Frontend | High |
| PW-013 | SEO: meta tags, Open Graph, sitemap.xml, robots.txt, Core Web Vitals optimization | Frontend | Medium |
| PW-014 | Reports page: public report PDFs downloadable; private reports require login | Frontend + Backend | Medium |

### Sprint 4 — Weeks 6–7: Member Management

| Story | Description | Owner | Priority |
| --- | --- | --- | --- |
| MM-001 | Member self-registration: full form (personal info, contact, mosque, category, photo upload, consent) | Frontend + Backend | High |
| MM-002 | Registration: Rwanda National ID format validation (16 digits); duplicate detection | Backend | High |
| MM-003 | Admin approval workflow: pending queue, approve/reject with reason, SMS+email notification | Backend + Frontend | High |
| MM-004 | Member profile page: avatar, personal info, edit capabilities, activity history | Frontend + Backend | High |
| MM-005 | Photo upload to S3 with crop tool; webcam capture on mobile | Frontend | Medium |
| MM-006 | Member categorization management by admin (Standard/Student/Scholar/Partner/VIP) | Backend + Frontend | High |
| MM-007 | Member list page: filterable by area, mosque, school, category, status; paginated (50/page) | Frontend + Backend | High |
| MM-008 | Member export to Excel and PDF | Backend | Medium |
| MM-009 | Digital member ID card — PDF generation with QR code; downloadable from portal | Backend | Medium |
| MM-010 | Member status management: Active/Inactive/Suspended/Deceased with reason and audit log | Backend | High |
| MM-011 | Bulk member import via CSV (SuperAdmin); validation report on import | Backend | Low |
| MM-012 | Member search: by name, national ID, phone, mosque, area | Backend + Frontend | High |

### Sprint 5 — Week 8: Mosque, Area & Prayer Times

| Story | Description | Owner | Priority |
| --- | --- | --- | --- |
| MOS-001 | Mosque registration: name, address, GPS coordinates, capacity, founding year, photos | Backend + Frontend | High |
| MOS-002 | Branch hierarchy: parent mosque → branch mosques (unlimited depth) | Backend | High |
| MOS-003 | Imam management: assign imam to mosque, imam profile, contact details, tenure dates | Backend + Frontend | High |
| MOS-004 | Mosque map view: all mosques on interactive map; filter by area; directions link | Frontend | Medium |
| MOS-005 | Area management: Province → District → Sector hierarchy; link to mosque and members | Backend + Frontend | High |
| MOS-006 | Mosque contact management: phone, email, opening hours, Friday prayer time | Backend | Medium |
| PT-001 | Prayer time calculation engine: Muslim World League method using coordinates | Backend | High |
| PT-002 | Mosque-specific prayer time adjustments (±minutes per prayer per mosque) | Backend | Medium |
| PT-003 | Prayer times public API: GET /api/v1/prayer-times?mosqueId=X or ?lat=&lng= | Backend | High |
| PT-004 | Weekly and monthly prayer schedule generation; PDF download | Backend | Medium |
| BLOG-001 | Blog: create/edit/publish posts; rich text editor; categories; tags; SEO fields | Frontend + Backend | Medium |
| GAL-001 | Gallery: photo/video upload; category filter; lightbox viewer | Frontend + Backend | Low |

## 2.3  Deliverables

| # | Deliverable | Status on Exit |
| --- | --- | --- |
| 1 | Full public website live at rmc.org.rw (all pages, 3 languages) | Deployed to production |
| 2 | Member registration, approval, and profile management system | Live — first real members registered |
| 3 | Mosque and branch management system with map | Live in staging; production ready |
| 4 | Prayer times API and public widget | Live — real prayer times displayed |
| 5 | Admin dashboard: member management, mosque management | Live for RMC admin team |
| 6 | Digital member ID card generation | Working; tested by PM and BA |
| 7 | Blog with first 5 articles published by RMC team | Live on website |
| 8 | API documentation (Swagger) for all Phase 2 endpoints | Published at /api/docs |

## 2.4  Quality Gate — Phase 2 Exit Criteria

| Check | Pass Condition |
| --- | --- |
| Public Website | All pages load in < 2s on 4G mobile; Lighthouse score > 85 on mobile |
| Multilingual | All pages fully translated; Arabic RTL renders correctly on Chrome and Safari |
| Member Registration | End-to-end registration tested: register → OTP → admin approve → member notified |
| Prayer Times | Prayer times for Kigali verified against IslamicFinder.org — within 2 minutes |
| Admin Dashboard | RMC admin can filter, view, approve, and export members without errors |
| Mobile Responsiveness | All pages tested at 375px, 768px, 1440px — no layout breaks |
| BA Sign-off | Business Analyst confirms all homepage and member management requirements met |
| Stakeholder Demo | Live demo given to RMC leadership; feedback documented and triaged |

| P3 | Services & Payment Integration |
| --- | --- |

| Attribute | Detail |
| --- | --- |
| Duration | Weeks 9 – 14 (6 weeks, 3 sprints) |
| Theme | All 7 community services with document workflows, fee management, and full payment integration |
| Goal | Community members can submit all service applications online, pay fees via MoMo/BK/Visa, and receive their certificates digitally. Admins can review, approve, and issue certificates from the dashboard. |
| Exit Milestone | First real marriage certificate application submitted, paid, reviewed, and issued entirely online without a physical visit |

## 3.1  Objectives

- Build marriage application workflow: document upload (IDs, photos, witness details), payment (RWF 30,000 mosque / RWF 200,000 out-of-mosque), admin review, certificate PDF generation with QR verification

- Build funeral service request workflow: emergency request form, imam assignment, logistics coordination

- Build good conduct certificate application: member verification, admin approval, 6-month expiry PDF certificate

- Build Hijra service request (clarify scope with stakeholder — assumed: migration/relocation support documentation)

- Build scholarship application: eligibility form, document upload, automated scoring, admin final approval

- Build tender application portal: RMC posts tenders, organizations apply, admin evaluates

- Build job application portal: RMC posts vacancies, applicants upload CV, admin manages shortlisting

- Integrate MTN Mobile Money (MoMo) payment: request-to-pay, webhook callback, idempotency

- Integrate BK Online payment gateway

- Integrate Stripe (Visa/Mastercard) for international donors

- Build payment receipt PDF auto-generation and email delivery

- Build certificate verification page (public QR scan URL)

## 3.2  Sprint Breakdown

### Sprint 6 — Weeks 9–10: Payment Infrastructure & Marriage Service

| Story | Description | Owner | Priority |
| --- | --- | --- | --- |
| PAY-001 | MTN MoMo sandbox integration: RequestToPay API, initiate payment, poll status | Backend Dev 1 | Critical |
| PAY-002 | MoMo webhook endpoint: receive SUCCESSFUL/FAILED callbacks, verify signature, update transaction | Backend Dev 1 | Critical |
| PAY-003 | Idempotency keys for all payment operations (prevent duplicate charges on retry) | Backend Dev 1 | Critical |
| PAY-004 | BK Online sandbox integration: payment initiation and callback handling | Backend Dev 2 | Critical |
| PAY-005 | Stripe sandbox integration: PaymentIntent, webhook (payment_intent.succeeded) | Backend Dev 2 | High |
| PAY-006 | Transaction ledger: record all payments with status, reference, method, amount, timestamps | Backend Dev 1 | Critical |
| PAY-007 | Payment receipt PDF: auto-generate on successful payment; email to payer; downloadable from portal | Backend Dev 2 | High |
| SVC-001 | Marriage application form: groom/bride details, witness details, guardian info, document uploads | Frontend Dev 1 | High |
| SVC-002 | Marriage application backend: validate inputs, validate file types/sizes, store to S3, create application record | Backend Dev 1 | High |
| SVC-003 | Marriage payment flow: present amount (30K or 200K), initiate MoMo/BK/Visa, wait for confirmation | Frontend + Backend | High |
| SVC-004 | Marriage admin review: pending applications list, document viewer, approve/request more docs/reject | Frontend Dev 2 + Backend | High |
| SVC-005 | Marriage certificate PDF generation: RMC-branded PDF with QR code, Arabic calligraphy header, all details | Backend Dev 2 | High |
| SVC-006 | Certificate verification page: public page at /verify/{code} — shows certificate validity and details | Backend + Frontend | High |

### Sprint 7 — Weeks 11–12: Remaining Services

| Story | Description | Owner | Priority |
| --- | --- | --- | --- |
| SVC-007 | Funeral service form: deceased details, family contact, location, urgency flag; imam notification | Backend + Frontend | High |
| SVC-008 | Funeral admin workflow: assign imam, schedule, mark completed, family notifications | Backend | High |
| SVC-009 | Good conduct certificate application: member details, purpose, admin review, PDF issuance, 6-month expiry | Backend + Frontend | High |
| SVC-010 | Hijra service application (stakeholder-confirmed scope: relocation support documentation request) | Backend + Frontend | Medium |
| SVC-011 | Scholarship application form: personal info, academic records upload, essay, references | Frontend Dev 1 | High |
| SVC-012 | Scholarship scoring engine: automated score based on defined criteria; ranking dashboard | Backend Dev 1 | High |
| SVC-013 | Scholarship admin workflow: review applications, override scores, approve/reject, notify applicants | Backend + Frontend | High |
| SVC-014 | Tender portal: admin posts tender (description, deadline, documents); organizations apply with proposal upload | Backend + Frontend | Medium |
| SVC-015 | Job application portal: admin posts vacancy; candidates apply with CV upload; admin shortlisting | Backend + Frontend | Medium |
| SVC-016 | Service application status page: member sees all their applications with current status and history | Frontend | High |

### Sprint 8 — Weeks 13–14: Payment Hardening & Production Activation

| Story | Description | Owner | Priority |
| --- | --- | --- | --- |
| PAY-008 | Switch MoMo from sandbox to production credentials; test with real phones (small amounts) | Backend Dev 1 + PM | Critical |
| PAY-009 | Switch BK Online to production; test with BK test accounts | Backend Dev 2 + PM | Critical |
| PAY-010 | Payment reconciliation job: BullMQ job runs hourly to check pending transactions, retry callbacks | Backend Dev 1 | High |
| PAY-011 | Refund management: admin initiates refund in dashboard; refund logged in audit trail | Backend Dev 2 | Medium |
| PAY-012 | Payment failure handling: user sees clear error message; application saved as draft for 48h | Frontend + Backend | High |
| PAY-013 | Rate limiting on payment endpoints: 10 requests/minute per user; block suspicious patterns | Backend Dev 1 | High |
| SVC-017 | SMS notifications for all service events: submitted, approved, rejected, certificate ready | Backend Dev 2 | High |
| SVC-018 | Email notifications for all service events with PDF attachments | Backend Dev 2 | High |
| SVC-019 | Admin reports: service applications by type, status, period; export to PDF/Excel | Backend Dev 1 | Medium |
| E2E-001 | End-to-end test: complete marriage application flow from form to certificate issuance (Playwright) | QA Engineer | Critical |
| E2E-002 | End-to-end test: payment failure → retry → success scenario | QA Engineer | Critical |

## 3.3  Payment Integration Detail

| Provider | Credential Type | Webhook | Test Method | Production Gate |
| --- | --- | --- | --- | --- |
| MTN MoMo | API User + API Key + Subscription Key | POST /api/v1/webhooks/momo | MTN Sandbox (simulated phone) | RMC signs MTN MoMo agreement; production keys obtained from MTN |
| BK Online | Merchant ID + Secret Key | POST /api/v1/webhooks/bk | BK Online sandbox portal | RMC has BK merchant account; production keys from BK |
| Stripe (Visa/MC) | Publishable Key + Secret Key | POST /api/v1/webhooks/stripe | Stripe test cards (4242...) | Stripe account in RWF; Stripe Dashboard production mode activated |

## 3.4  Quality Gate — Phase 3 Exit Criteria

| Check | Pass Condition |
| --- | --- |
| Payment Integration | All 3 payment providers tested with real/simulated transactions; webhooks verified; no duplicate charges in 100-transaction test |
| Marriage Service | Full flow (submit → pay → admin review → certificate → QR verify) completed by QA with zero errors |
| All 7 Services | Each service: form submission, document upload, admin action, and notification tested and signed off by BA |
| Certificate QR | Public certificate verification URL works; forged QR code rejected |
| SMS & Email | All service notification triggers tested; SMS delivered < 60s; email delivered < 5 min |
| Security | Payment endpoints rate-limited; webhook signatures verified; SQL injection tests pass (OWASP ZAP quick scan) |
| Stakeholder Demo | RMC executive secretary demonstrates applying for a marriage certificate live; approves the flow |

| P4 | Donation & Financial Management |
| --- | --- |

| Attribute | Detail |
| --- | --- |
| Duration | Weeks 15 – 18 (4 weeks, 2 sprints) |
| Theme | Transparent donation campaigns, Zakat management, orphan sponsorship, financial tracking, and donor impact reporting |
| Goal | Community members and diaspora donors can contribute to any campaign online; Zakat is calculated and tracked transparently; financial reports are available to leadership; donors receive impact updates on their contributions |
| Exit Milestone | First online donation campaign receives 10 test donations via all 3 payment methods; Zakat fund balance is tracked separately; donor receives impact report PDF |

## 4.1  Objectives

- Build donation campaign management: create campaigns with target amounts, timelines, images, and real-time progress bars

- Implement Zakat calculator on public website (inputs: cash, gold, silver, trade goods; output: Zakat due at 2.5%)

- Build Zakat collection and distribution ledger (8 Quranic categories; immutable distribution records)

- Implement orphan sponsorship program: individual child profiles, monthly recurring payments, quarterly impact reports with photos

- Build Quran program giving with class enrollment tracking and donor-specific progress updates

- Implement recurring donation setup (monthly, quarterly, annual) with automated payment and advance notification

- Build auto-generated donation receipts (PDF, emailed, downloadable)

- Build donor impact report generation: admin uploads evidence (photos, beneficiary count); system generates report and emails all campaign donors

- Build financial management module: income/expense recording, fund allocation, budget tracking

- Build financial reports: income statement, fund summary, Zakat distribution, donor report — exportable as PDF and Excel

- Implement audit log for all financial operations (immutable; 7-year retention)

## 4.2  Sprint Breakdown

### Sprint 9 — Weeks 15–16: Donations & Zakat

| Story | Description | Owner | Priority |
| --- | --- | --- | --- |
| DON-001 | Donation campaign CRUD: title, description, target amount, start/end date, hero image, progress bar | Frontend + Backend | High |
| DON-002 | Campaign public page: real-time progress bar, donor count, recent donors (opt-in), share buttons | Frontend | High |
| DON-003 | One-off donation flow: select campaign → choose amount → choose payment method → pay → receipt | Frontend + Backend | Critical |
| DON-004 | Anonymous donation option: name withheld from public but recorded internally | Backend | Medium |
| DON-005 | Recurring donation setup: select frequency (monthly/quarterly/annual), amount, payment method; stored securely | Backend | High |
| DON-006 | Recurring payment trigger: BullMQ scheduled job; 3-day advance SMS notice; auto-charge on date | Backend | High |
| DON-007 | Donation receipt PDF: RMC logo, donor name, amount, date, campaign, transaction ID, QR | Backend | High |
| DON-008 | Zakat calculator: public tool on website; inputs for all asset categories; nisab threshold (gold price API) | Frontend + Backend | High |
| DON-009 | Zakat payment: calculator result → one-click donation to Zakat fund | Frontend + Backend | High |
| DON-010 | Zakat distribution ledger: admin records distribution; category (8 Quranic types); beneficiary details | Backend + Frontend | High |
| DON-011 | Orphan profile creation: name, photo, age, background story, monthly sponsorship cost | Backend + Frontend | High |
| DON-012 | Orphan sponsorship payment: select child → recurring monthly payment → donor receives quarterly update | Frontend + Backend | High |
| DON-013 | Quran program: donor sponsors N students; admin records class progress; donor receives updates | Backend + Frontend | Medium |
| DON-014 | Donor impact report: admin uploads photos/data; PDF auto-generated; emailed to all campaign donors | Backend | High |

### Sprint 10 — Weeks 17–18: Financial Management

| Story | Description | Owner | Priority |
| --- | --- | --- | --- |
| FIN-001 | Income recording: all donation transactions auto-flow to income ledger with category | Backend | Critical |
| FIN-002 | Expense recording: admin enters expense (vendor, amount, category, receipt photo upload, approver) | Backend + Frontend | High |
| FIN-003 | Dual approval: expenses > RWF 1,000,000 require second admin to approve before posting | Backend | High |
| FIN-004 | Fund management: General Fund, Zakat Fund, Orphan Fund, Education Fund — real-time balances | Backend + Frontend | High |
| FIN-005 | Inter-fund transfers: move money between funds; dual approval; audit logged | Backend | Medium |
| FIN-006 | Budget management: define annual budget lines per department/program; actual vs budget variance | Backend + Frontend | Medium |
| FIN-007 | Financial dashboard: income vs expense chart (monthly/quarterly/annual); fund balance summary | Frontend | High |
| FIN-008 | Income statement report export (PDF + Excel): configurable date range | Backend | High |
| FIN-009 | Zakat distribution report: who received, when, amount, category — PDF export | Backend | High |
| FIN-010 | Donor report: per-campaign donor list with amounts; anonymous donors excluded | Backend | High |
| FIN-011 | Audit log viewer (Admin+): filter by entity, action, user, date range; non-editable | Backend + Frontend | Critical |
| FIN-012 | Budget alert: auto-email to Admin when fund reaches 80% of budget; auto-block at 100% | Backend | Medium |

## 4.3  Quality Gate — Phase 4 Exit Criteria

| Check | Pass Condition |
| --- | --- |
| Donation Campaigns | End-to-end donation tested via all 3 payment methods; receipt emailed and downloadable |
| Recurring Payments | Scheduled job runs on correct dates; 3-day advance notice sent; charge processed |
| Zakat Calculator | Calculation verified by Islamic finance scholar on RMC team; nisab threshold correct |
| Orphan Sponsorship | Sponsor linked to specific child; recurring payment active; quarterly report flow tested |
| Financial Reports | Income statement, fund summary, Zakat report generated as PDF and Excel without error |
| Audit Log | Every financial operation (create/update/delete) appears in audit log; log is non-editable |
| Dual Approval | Expense > 1M RWF cannot be posted without second approver; tested by BA |
| Donor Impact Report | Admin uploads photos; report generated; emailed to all campaign donors — tested end-to-end |

| P5 | Events, Communication & Notifications |
| --- | --- |

| Attribute | Detail |
| --- | --- |
| Duration | Weeks 19 – 21 (3 weeks, 1.5 sprints) |
| Theme | Community engagement through events, multi-channel messaging, and real-time notifications |
| Goal | RMC can create events, manage registrations, and communicate with members via SMS, email, push notifications, and internal notifications — all from one admin interface |
| Exit Milestone | Announcement broadcast sent to 100 test members via SMS and email simultaneously; event registration open and accepting sign-ups |

## 5.1  Objectives

- Build event management: create events, registration, attendance tracking, QR-code check-in

- Build announcement system: admin creates announcements; targeted to all/area/mosque/category; auto-published to website

- Implement SMS notification service (MTN/Airtel API); BullMQ queue for batch sends

- Implement email notification service (SMTP/SendGrid); HTML templates per notification type

- Implement push notifications (Firebase Cloud Messaging) for PWA/Android

- Build internal notification center: bell icon with unread count; notification history

- Build WebSocket real-time updates: live donation counter, live event registration count

- Implement notification preferences: member can opt-in/out per channel and notification type

## 5.2  Sprint Breakdown

### Sprint 11 — Weeks 19–21: Events & All Communications

| Story | Description | Owner | Priority |
| --- | --- | --- | --- |
| EVT-001 | Event CRUD: title, description, date/time, location, mosque, capacity, registration deadline, event image | Backend + Frontend | High |
| EVT-002 | Event registration: member registers for event; confirmation SMS/email; capacity tracking | Backend + Frontend | High |
| EVT-003 | Event attendance: QR code per registration; admin scans at entry; attendance count live | Backend + Frontend | Medium |
| EVT-004 | Event calendar view: monthly calendar on website with event pins; filter by type/mosque | Frontend | Medium |
| EVT-005 | Event reminder: automatic SMS/email 24h before event to registered attendees | Backend | High |
| ANN-001 | Announcement CRUD: title, content, priority, start/end dates, target (all/area/mosque/category) | Backend + Frontend | High |
| ANN-002 | Announcement auto-publish to homepage ticker and announcements page | Frontend | High |
| ANN-003 | Announcement broadcast: admin clicks "Send to members" → bulk SMS + email via BullMQ | Backend | High |
| SMS-001 | SMS service integration (MTN/Airtel API via Africa's Talking or direct) | Backend | Critical |
| SMS-002 | SMS BullMQ queue: batch sender; retry on failure; delivery status tracking | Backend | High |
| SMS-003 | SMS templates per event type (registration, approval, reminder, announcement) in 3 languages | Backend | High |
| EMAIL-001 | Email service (SMTP/SendGrid): HTML templates with RMC branding per notification type | Backend | High |
| EMAIL-002 | Email queue: BullMQ; retry on soft bounce; hard bounce handling; unsubscribe link | Backend | High |
| PUSH-001 | Firebase Cloud Messaging setup; service worker for PWA; push notification on web and Android | Backend + Frontend | High |
| PUSH-002 | Push notification topics: prayer-times, announcements, events, donations — member subscribes per topic | Backend + Frontend | Medium |
| NOTIF-001 | Internal notification center: bell icon, unread count badge, notification list, mark as read | Frontend + Backend | High |
| NOTIF-002 | Notification preferences page: member controls which channels (SMS/email/push) per event type | Frontend + Backend | Medium |
| WS-001 | WebSocket (Socket.IO): live donation campaign counter; real-time event registration updates | Backend + Frontend | Low |

## 5.3  Quality Gate — Phase 5 Exit Criteria

| Check | Pass Condition |
| --- | --- |
| Event Registration | End-to-end: create event → member registers → confirmation SMS and email received |
| QR Check-in | Admin scans QR code on mobile → attendance marked; works offline for 30 minutes |
| Bulk SMS | Broadcast to 100 test members; all receive SMS within 60 seconds; delivery report shows 95%+ |
| Email Templates | All email templates tested on Gmail, Outlook, mobile; no broken images or layout |
| Push Notifications | Push delivered to PWA (Chrome Android) and Safari (iOS) within 5 seconds of trigger |
| Unsubscribe | Member clicks email unsubscribe → removed from that notification type immediately |
| WebSocket | Live donation counter updates in real-time in a second browser tab on same campaign page |
| Load Test | 10 simultaneous bulk SMS sends of 50 messages each — queue processes all without errors |

| P6 | Analytics, Reports & AI Assistant |
| --- | --- |

| Attribute | Detail |
| --- | --- |
| Duration | Weeks 22 – 26 (5 weeks, 2–3 sprints) |
| Theme | Data-driven leadership insights and AI-powered 24/7 community assistant |
| Goal | RMC leadership has real-time dashboards with KPIs; donors see impact reports; the AI assistant answers community questions in Kinyarwanda, English, and Arabic around the clock |
| Exit Milestone | AI chatbot correctly answers 20 test Islamic and RMC-specific questions in all 3 languages; SuperAdmin sees live analytics dashboard with all key metrics |

## 6.1  Objectives

- Build admin analytics dashboard: total members, active members, new registrations trend, donations trend, service applications by type, mosque coverage map

- Build public statistics dashboard (homepage): animated counters with real-time updates

- Build report scheduler: admin configures reports (monthly financial summary, donor report, member statistics) to auto-generate and email to specified recipients

- Build advanced donor portal: donation history, impact reports, downloadable receipts, orphan sponsorship status

- Implement Elasticsearch/OpenSearch OR PostgreSQL full-text search — evaluated based on data volume (threshold: 50,000 records)

- Build AI assistant (RAG architecture): Claude API primary, knowledge base in pgvector, LangChain orchestration

- Build knowledge base admin interface: admin adds/edits/deletes knowledge base entries; AI uses these for grounded responses

- Implement AI content moderation: flag inappropriate queries; human review queue

- Implement AI usage analytics: queries per day, satisfaction ratings, top questions, unanswered queries

## 6.2  Sprint Breakdown

### Sprint 12 — Weeks 22–23: Analytics & Reports

| Story | Description | Owner | Priority |
| --- | --- | --- | --- |
| ANA-001 | Admin KPI dashboard: members (total/active/new/by category), mosques covered, donations (total/monthly/by campaign) | Frontend + Backend | High |
| ANA-002 | Financial analytics: income vs expense trend chart (12-month); fund balances; Zakat in/out | Frontend + Backend | High |
| ANA-003 | Service analytics: applications by type, approval rates, average processing time | Frontend + Backend | Medium |
| ANA-004 | Donor analytics: donor count, retention rate, average donation, top campaigns | Frontend + Backend | Medium |
| ANA-005 | Geographic analytics: member density map by area/district; mosque coverage heat map | Frontend + Backend | Medium |
| ANA-006 | Public statistics page: animated counters (members, mosques, beneficiaries, donations); updated daily | Frontend | High |
| RPT-001 | Report scheduler: admin defines report type, frequency, recipients; auto-runs and emails PDF | Backend | High |
| RPT-002 | Monthly financial summary auto-report: income statement + fund balances + Zakat summary PDF | Backend | High |
| RPT-003 | Donor impact report template: campaign photos, beneficiary count, funds used — admin fills template | Backend + Frontend | High |
| RPT-004 | Member statistics report: by area, mosque, category, age group — PDF + Excel | Backend | Medium |
| SRCH-001 | Evaluate data volume; implement PostgreSQL FTS if < 50K records; OpenSearch if needed | Backend | Medium |
| SRCH-002 | Unified search: member profiles, blog posts, services, events, announcements — single search bar | Frontend + Backend | Medium |

### Sprint 13 — Weeks 24–26: AI Assistant

| Story | Description | Owner | Priority |
| --- | --- | --- | --- |
| AI-001 | pgvector extension enabled on PostgreSQL; knowledge_base_entries table with embedding column | DB Engineer + Backend | High |
| AI-002 | Knowledge base seed: import RMC services guide, prayer info, Zakat rules, FAQs — generate embeddings | Backend Dev 1 | High |
| AI-003 | Embedding generation pipeline: on knowledge base entry create/update, generate OpenAI embedding, store in pgvector | Backend Dev 1 | High |
| AI-004 | RAG pipeline: embed user query → pgvector similarity search → retrieve top 5 contexts → build prompt → Claude API | Backend Dev 1 | Critical |
| AI-005 | Language detection: auto-detect Kinyarwanda/English/Arabic; respond in same language | Backend Dev 1 | High |
| AI-006 | Streaming response: stream Claude API response via WebSocket to frontend; typing indicator UX | Backend + Frontend Dev 1 | High |
| AI-007 | Chat UI: floating chat widget (all pages); chat panel; message history; thumbs up/down feedback | Frontend Dev 2 | High |
| AI-008 | Session management: chat session persists for 24h; user can view past sessions | Backend | Medium |
| AI-009 | AI rate limiting: 30 queries/hour per user; 5/minute burst; clear error on limit | Backend Dev 1 | High |
| AI-010 | Content moderation: safety classifier before sending to LLM; block harmful queries | Backend Dev 1 | High |
| AI-011 | Knowledge base admin UI: list entries, add/edit/delete; re-embed on change; category management | Frontend Dev 2 + Backend Dev 2 | High |
| AI-012 | AI analytics: queries per day, satisfaction score, top 20 questions, unanswered queries list | Backend Dev 2 + Frontend Dev 2 | Medium |
| AI-013 | Fallback: if Claude API unavailable, serve top 10 FAQ answers from knowledge base directly | Backend Dev 1 | High |
| AI-014 | Prompt engineering: system prompt enforces factual responses; prohibits fabricating Islamic rulings; language-consistent | Backend Dev 1 | Critical |

## 6.3  AI Knowledge Base — Initial Content Plan

| Category | Articles to Create | Who Writes | Priority |
| --- | --- | --- | --- |
| RMC Services | How to apply for each of the 7 services; fees; timelines; required documents | BA + Admin | High |
| Prayer & Islam | Prayer times explanation; how Zakat is calculated; Islamic calendar; key dates | Imam / Scholar | High |
| Donations | How donations are used; impact stories; how to set up recurring giving | Finance Admin | High |
| Organization | About RMC; leadership structure; programs; partner organizations; contact details | Admin | High |
| Scholarships | Eligibility criteria; application process; what is covered; past recipients | Education Admin | Medium |
| Orphan Program | How sponsorship works; what funds cover; how to see child updates | Programs Admin | Medium |
| Events | How to register for events; upcoming events summary; how to volunteer | Events Admin | Medium |
| FAQ | Most common questions from past inquiries (compile from current office records) | BA + Admin | High |

## 6.4  Quality Gate — Phase 6 Exit Criteria

| Check | Pass Condition |
| --- | --- |
| Analytics Dashboard | All KPI widgets display real data; charts load < 2 seconds; data is accurate vs database counts |
| Report Scheduler | Scheduled monthly report generates and emails correctly on test trigger; PDF is well-formatted |
| AI — Accuracy | AI answers 18/20 test questions correctly; 2 allowed to be "I don't have information on that" |
| AI — Language | Same question asked in Kinyarwanda, English, Arabic → correct language response each time |
| AI — Safety | 10 inappropriate/harmful test queries → all blocked; none reach Claude API |
| AI — Hallucination | AI does not fabricate Quranic verses or Islamic rulings not in knowledge base (tested by Islamic scholar) |
| AI — Performance | AI response time (first token) < 3 seconds on standard query; streaming visible immediately |
| Search | Search returns relevant results for member names, blog posts, and services within 1 second |

| P7 | Mobile PWA, Schools Module & Optimization |
| --- | --- |

| Attribute | Detail |
| --- | --- |
| Duration | Weeks 27 – 30 (4 weeks, 2 sprints) |
| Theme | Mobile-first accessibility, student/school management, performance optimization, and offline capability |
| Goal | Community members can install RMC as a mobile app on Android; rural users with intermittent connectivity can still access core features offline; students and schools are managed digitally |
| Exit Milestone | PWA installed on 5 test Android devices; app works offline for prayer times and member profile; submitted to Google Play Store |

## 7.1  Objectives

- Complete PWA implementation: service worker, offline cache strategy, install prompt, app manifest

- Submit to Google Play Store via Trusted Web Activity (TWA) wrapper

- Implement offline-capable features: prayer times (pre-cached 7 days), member profile view, donation status

- Build schools management module: school registration, class management, student enrollment, attendance, academic records

- Link students to scholarship module and member profiles

- Implement Qibla direction feature in mobile app (device compass API)

- Implement Islamic Hijri calendar alongside Gregorian calendar

- Performance optimization: code splitting, image optimization, lazy loading, Redis caching for frequent queries

- Accessibility audit and remediation: WCAG 2.1 AA compliance (axe-core + manual review)

- Final database optimization: query analysis, missing index identification, slow query resolution

## 7.2  Sprint Breakdown

### Sprint 14 — Weeks 27–28: PWA & Mobile

| Story | Description | Owner | Priority |
| --- | --- | --- | --- |
| PWA-001 | Service worker: cache-first for static assets; network-first for API; offline fallback page | Frontend Dev 1 | Critical |
| PWA-002 | Web app manifest: name, icons (192px, 512px), theme color, display: standalone, start_url | Frontend Dev 1 | Critical |
| PWA-003 | Add to Home Screen install prompt: triggered after 2nd visit; dismissible; re-prompt after 30 days | Frontend Dev 1 | High |
| PWA-004 | Offline prayer times: pre-cache 7-day schedule for user's mosque on every sync | Frontend Dev 1 | High |
| PWA-005 | Offline member profile: cache own profile data; show banner "You are offline — some features limited" | Frontend Dev 1 | High |
| PWA-006 | Background sync: queue actions taken offline (donation intent, service application draft); sync when online | Frontend Dev 1 | Medium |
| TWA-001 | Build Trusted Web Activity (TWA) wrapper for Google Play Store | Frontend Dev 2 | High |
| TWA-002 | Play Store assets: screenshots (8), feature graphic, description in English and Kinyarwanda | PM + Designer | High |
| TWA-003 | Submit to Google Play Store internal testing track; invite 20 testers | PM | High |
| MOB-001 | Qibla direction: device compass API; arrow points to Mecca; works offline | Frontend Dev 2 | Medium |
| MOB-002 | Islamic calendar widget: Hijri date display alongside Gregorian; Islamic event markers | Frontend Dev 2 | Medium |
| MOB-003 | Mobile-specific optimizations: touch targets 44px min; swipe gestures on carousel; haptic feedback on PWA | Frontend Dev 1 | High |

### Sprint 15 — Weeks 29–30: Schools Module & Performance

| Story | Description | Owner | Priority |
| --- | --- | --- | --- |
| SCH-001 | School registration: name, location, mosque affiliation, principal, contact, founding year | Backend + Frontend | High |
| SCH-002 | Class management: class name, level, academic year, teacher, room, schedule | Backend + Frontend | High |
| SCH-003 | Student enrollment: link member_profile (student category) to school and class; enrollment date | Backend + Frontend | High |
| SCH-004 | Student attendance: daily attendance marking by class teacher; monthly attendance report | Backend + Frontend | Medium |
| SCH-005 | Academic records: grades, assessments, academic year summary per student | Backend + Frontend | Medium |
| SCH-006 | Link students to scholarship applications: eligibility auto-populated from academic record | Backend | High |
| SCH-007 | Schools dashboard: admin sees all schools, classes, enrollment counts, attendance rates | Frontend + Backend | Medium |
| PERF-001 | Redis caching: prayer times (24h TTL), homepage stats (1h TTL), member count (15min TTL) | Backend Dev 1 | High |
| PERF-002 | Next.js optimization: Image component for all images; lazy loading below fold; code splitting per route | Frontend Dev 1 | High |
| PERF-003 | Database query analysis: EXPLAIN ANALYZE on top 20 queries; add missing indexes; optimize N+1 queries | DB Engineer | High |
| PERF-004 | CDN configuration: CloudFront for static assets; correct cache headers; cache invalidation on deploy | DevOps | High |
| ACCESS-001 | Accessibility audit: axe-core automated scan; manual keyboard navigation; screen reader test (NVDA) | QA + Frontend Dev 2 | High |
| ACCESS-002 | Remediate all WCAG 2.1 AA violations found in ACCESS-001 | Frontend Dev 2 | High |

## 7.3  Quality Gate — Phase 7 Exit Criteria

| Check | Pass Condition |
| --- | --- |
| PWA Install | PWA installable on 5 different Android devices (Chrome); loads from home screen correctly |
| Offline Mode | Prayer times and member profile accessible with airplane mode enabled |
| Play Store | App submitted to internal testing track; 5 testers install and test successfully |
| Schools Module | School → class → student → attendance → academic record full workflow tested by QA |
| Scholarship Link | Student academic record auto-populates scholarship application eligibility fields |
| Performance | Lighthouse scores: Performance > 85, Accessibility > 90, SEO > 95, Best Practices > 90 (mobile) |
| Accessibility | axe-core: 0 critical violations; keyboard navigation tested on all critical pages; 4.5:1 contrast ratio confirmed |
| Redis Caching | Homepage loads in < 1s on repeat visit (cache hit); prayer times API returns < 50ms (cached) |

| P8 | Testing, Security Audit, Launch & Training |
| --- | --- |

| Attribute | Detail |
| --- | --- |
| Duration | Weeks 31 – 34 (4 weeks — the most critical phase) |
| Theme | Quality assurance, security hardening, stakeholder acceptance, staff training, and controlled go-live |
| Goal | The platform is fully tested, secure, compliant with NCSA/DPP requirements, all staff are trained, and the system is live for the full RMC community with a monitored soft launch |
| Exit Milestone | System is live at rmc.org.rw; first 100 real members registered; first real donation received; all staff can perform their roles independently |

## 8.1  Objectives

- Complete full end-to-end regression testing of all features across all 7 phases

- Conduct penetration testing (external security consultant) covering OWASP Top 10

- Conduct User Acceptance Testing (UAT) with real RMC stakeholders from each user group

- Prepare and submit NCSA/DPP compliance documentation (Data Protection Impact Assessment, Privacy Policy, DPO appointment)

- Execute performance load test: 10,000 concurrent users; Ramadan peak simulation

- Conduct training sessions for all user groups: SuperAdmin, Admin, Mosque Operators

- Prepare all go-live materials: deployment runbook, rollback plan, incident response plan

- Execute staged go-live: pilot (1 mosque) → soft launch (Kigali mosques) → full national launch

- Establish post-launch support protocol: 2-week hypercare period with daily standups

## 8.2  Week-by-Week Plan

### Week 31 — Full Regression & Security Testing

| Activity | Description | Owner | Exit Condition |
| --- | --- | --- | --- |
| Regression Test — Auth | Re-test all auth scenarios; check for regressions from Phase 7 changes | QA Engineer | All 20 auth test cases pass |
| Regression Test — Services | Re-test all 7 service workflows including payment integration | QA Engineer | All service E2E tests pass; 0 critical bugs |
| Regression Test — Donations | Re-test campaigns, Zakat, orphan, recurring, financial reports | QA Engineer | All donation scenarios pass; receipts correct |
| Regression Test — AI | Re-test 20 knowledge base questions; safety filters; language detection | QA Engineer | 18/20 pass; 0 safety bypass |
| Cross-browser Test | Chrome, Firefox, Safari (desktop + mobile); Edge; Samsung Internet | QA + Frontend | No critical layout or functional breaks |
| Penetration Test | External consultant: OWASP ZAP + manual; SQL injection; XSS; auth bypass; CSRF | Security Consultant | No critical findings; high findings remediated |
| Security Hardening | Remediate all pen test findings; retest; sign-off | Backend + DevOps | Security consultant signs off on remediated report |
| Data Privacy Audit | Review all PII handling; confirm consent flows; test right-to-erasure | BA + Tech Lead | DPP compliance checklist 100% complete |

### Week 32 — Performance Testing & UAT

| Activity | Description | Owner | Exit Condition |
| --- | --- | --- | --- |
| Load Test — Normal | k6: 1,000 concurrent users across all endpoints for 30 minutes | DevOps + QA | P95 < 500ms; 0 errors; no auto-scale failures |
| Load Test — Peak | k6: 10,000 concurrent users; auto-scaling triggers; monitor DB connections | DevOps + QA | Auto-scale triggers at correct threshold; no crash |
| Ramadan Simulation | k6: spike to 50,000 users over 2 hours; test CDN + caching behavior | DevOps | CDN absorbs static load; API stable; response < 2s P95 |
| UAT — RMC Members | 5 real community members test registration, donation, prayer times, AI | PM + BA | All 5 complete without assistance; feedback positive |
| UAT — Mosque Operators | 3 mosque administrators test member management, event creation, reporting | PM + BA | Operators complete tasks without assistance; confusion points documented |
| UAT — Admin Team | RMC HQ staff test service approvals, financial reports, communication | PM + BA | All workflows completed; admin team approves system |
| UAT — Diaspora Donor | 2 overseas donors test Visa payment, donation, impact report viewing | PM + BA | Payments succeed; receipts received; donor satisfied |
| UAT Sign-off | Business Analyst compiles UAT report; PM presents to RMC leadership; formal sign-off | BA + PM | RMC leadership signs UAT acceptance form |

### Week 33 — Training

| Training Session | Audience | Content | Format | Duration |
| --- | --- | --- | --- | --- |
| SuperAdmin Training | IT/Operations Manager (1-2 people) | System config, user management, audit logs, DB backup check, security settings, API management | Hands-on workshop | 1 full day |
| Admin Training | RMC HQ Staff (5-10 people) | Member management, service approvals, financial management, report generation, announcement creation, AI knowledge base | Workshop + manual | 2 full days |
| Mosque Operator Training | Mosque Administrators (20-50 people in batches) | Member registration, attendance, local events, donation recording, basic reports | Workshop + Kinyarwanda manual | 1 full day per batch |
| Imam Training | Imams and senior mosque staff | Prayer time management, mosque profile, announcements, member communications | Short session + video guide | Half day |
| End-User Awareness | General community members (via mosque announcement) | How to register, how to donate, how to use AI assistant, how to apply for services | Mosque announcement + WhatsApp video | Self-service |
| Training Material Creation | — | User manual (Kinyarwanda + English), Admin manual, Quick reference cards, Training videos (Kinyarwanda) | Documents + video | Week 33 parallel task |

### Week 34 — Staged Go-Live

| Stage | Description | Duration | Success Criteria | Rollback Trigger |
| --- | --- | --- | --- | --- |
| Pilot Launch | Go live for 1 mosque (Kigali Grand Mosque or RMC HQ); 50 selected members invited | Days 1–2 | 50 users active; 0 critical bugs; payments working; monitoring green | Any payment failure or data loss → rollback |
| Soft Launch | Open to all Kigali-based mosques; social media announcement | Days 3–5 | 500+ registrations; donation campaign live; AI assistant active; no system issues | Critical bug affecting > 10% users → rollback |
| National Launch | Open to all RMC members and mosques across Rwanda; press release | Day 6–7 | All mosque operators active; full team monitoring; communication team ready | Major outage → rollback; scale issue → scale-up |
| Hypercare (2 weeks) | Daily standup at 08:00; PM monitors dashboards; all developers on call; bugs triaged within 4 hours | Weeks 35–36 | < 5 bugs/day by end of hypercare; zero P1 incidents outstanding | — |

## 8.3  NCSA / DPP Compliance Deliverables

| Document | Description | Owner | Deadline |
| --- | --- | --- | --- |
| Privacy Policy | Public-facing policy: what data is collected, how used, retention periods, user rights, contact for data requests | BA + Legal | Week 31 |
| Data Protection Impact Assessment (DPIA) | Risk assessment of personal data processing; mitigations documented | BA + Tech Lead + Security | Week 31 |
| Data Processing Register | Register of all personal data processing activities; lawful basis for each | BA | Week 31 |
| DPO Appointment | Nominate Data Protection Officer; register with NCSA | RMC Leadership | Week 32 |
| Consent Records Architecture | Technical implementation of consent storage; audit trail of consent given/withdrawn | Backend Dev | Week 31 |
| Incident Response Plan | Steps to take in case of data breach; NCSA notification within 72 hours | Security + PM + Tech Lead | Week 33 |
| Vendor Data Processing Agreements (DPA) | Agreements with AWS, SendGrid, Stripe, Anthropic/Claude for data processing | PM + Legal | Week 32 |

## 8.4  Go-Live Checklist

| Category | Check Item | Owner | Status |
| --- | --- | --- | --- |
| Infrastructure | All EC2 instances in Auto Scaling Group; min 2 instances running | DevOps | Pre-launch |
| Infrastructure | RDS Multi-AZ enabled; latest snapshot verified | DevOps | Pre-launch |
| Infrastructure | CloudFront CDN live; static assets cached; cache invalidation working | DevOps | Pre-launch |
| Infrastructure | SSL certificates valid; auto-renewal configured; HSTS enabled | DevOps | Pre-launch |
| Security | All pen test findings closed or formally accepted by leadership | Security + PM | Pre-launch |
| Security | Secrets rotated from staging to production values (all API keys, passwords) | DevOps + Tech Lead | Day of launch |
| Security | Rate limiting active on all public endpoints; MFA active for all admin accounts | Tech Lead | Pre-launch |
| Payments | MoMo production credentials active; test payment of RWF 500 made and refunded | Backend Dev + PM | Day of launch |
| Payments | BK Online production active; test transaction verified | Backend Dev + PM | Day of launch |
| Payments | Stripe live mode active; webhooks pointing to production URL | Backend Dev | Day of launch |
| Communications | SMS production API active; test SMS sent to 5 phones | Backend Dev | Day of launch |
| Communications | Email: SPF, DKIM, DMARC records set; test email delivered, not in spam | DevOps | Pre-launch |
| AI | Claude API production key active; knowledge base fully populated (min 50 entries) | AI Lead | Pre-launch |
| Monitoring | All Grafana alerts active; Sentry error tracking live; SMS alert on down | DevOps | Pre-launch |
| Backup | Daily backup running; restore tested; cross-region copy active | DevOps | Pre-launch |
| Legal | Privacy Policy published on website; Cookie consent banner live | BA + Legal | Pre-launch |
| Training | All admin and operator training completed; manuals distributed | PM | Pre-launch |
| Rollback | Rollback plan documented and tested; team knows procedure | DevOps + PM | Pre-launch |

## 8.5  Quality Gate — Phase 8 (Final Acceptance)

| Check | Pass Condition |
| --- | --- |
| Penetration Test | External security consultant issues clear report; all critical/high findings remediated and retested |
| Load Test | 10,000 concurrent users: P95 < 500ms; 0 application crashes; auto-scaling works |
| UAT Sign-off | RMC leadership formally signs UAT acceptance document |
| NCSA Compliance | All DPP documents completed; Privacy Policy live; DPO appointed |
| Training Completion | 100% of admin and operator staff trained; training sign-off sheets completed |
| Monitoring Live | All Grafana dashboards active; at least 3 test alerts triggered and received |
| Zero Critical Bugs | No P1 or P2 open bugs at go-live; P3/P4 bugs logged in backlog |
| Payments Live | All 3 payment providers processing real transactions; receipts generated |
| Pilot Success | Pilot mosque runs for 48 hours without incidents; pilot users report satisfaction |

# POST-LAUNCH PLAN (Weeks 35–52)

The go-live is not the end — it is the beginning of the platform's operational life. The following post-launch activities ensure the platform stabilizes, grows, and continues improving.

## Hypercare Period (Weeks 35–36)

| Activity | Frequency | Owner |
| --- | --- | --- |
| Daily standup: overnight issues, bugs, user feedback | Daily 08:00 | PM |
| Bug triage: P1 fixed same day; P2 within 48h; P3 in next sprint | Daily | Tech Lead |
| User support: dedicated email and WhatsApp for admin questions | Real-time (9am–6pm) | BA + DevOps |
| Platform metrics review: registrations, donations, active users, errors | Daily | PM + DevOps |
| Stakeholder status email | Daily | PM |

## Stabilization Period (Weeks 37–44)

| Activity | Frequency | Owner |
| --- | --- | --- |
| 2-week sprints: fix bugs from user feedback; minor UX improvements | Per sprint | Full team |
| Weekly metrics report to RMC leadership | Weekly | PM |
| Monthly security review: check Sentry, audit logs, failed login attempts | Monthly | Tech Lead + DevOps |
| Monthly backup restoration test | Monthly | DevOps |
| Quarterly penetration test (lightweight) | Quarterly | Security Consultant |
| User feedback collection: survey to active members (NPS) | Monthly | BA |
| Knowledge base expansion: add 10 new AI knowledge articles | Monthly | Admin + BA |

## Growth & Enhancement (Weeks 45–52)

| Enhancement | Priority | Estimated Effort |
| --- | --- | --- |
| WhatsApp Business API integration for notifications | High | 3 weeks |
| USSD channel: basic prayer times and donation via USSD (*RMC#) | Medium | 4 weeks |
| Multi-currency support (USD, EUR) for diaspora donors | High | 2 weeks |
| Volunteer management module: register volunteers, assign to events | Low | 3 weeks |
| Islamic library: searchable Quran, Hadith summaries, fatwa database | Medium | 4 weeks |
| Diaspora portal: dedicated UI for overseas community members | Medium | 3 weeks |
| Advanced AI: voice input for prayer time queries; audio Quran | Low | 5 weeks |
| Play Store rating campaign: in-app prompt after 5 sessions | Low | 1 week |

# MASTER TIMELINE OVERVIEW

| Phase | Title | Weeks | Sprint(s) | Key Milestone |
| --- | --- | --- | --- | --- |
| 1 | Environment & Foundation Setup | 1–3 | S1–S2 | CI/CD live; Auth system deployed to staging |
| 2 | Core Platform & Member Management | 4–8 | S3–S5 | Public website live; first members registered |
| 3 | Services & Payment Integration | 9–14 | S6–S8 | All services live; real payments processing |
| 4 | Donation & Financial Management | 15–18 | S9–S10 | First donation campaign live; Zakat tracked |
| 5 | Events, Communication & Notifications | 19–21 | S11 | Bulk SMS live; push notifications working |
| 6 | Analytics, Reports & AI Assistant | 22–26 | S12–S13 | AI chatbot live; dashboards operational |
| 7 | Mobile PWA, Schools & Optimization | 27–30 | S14–S15 | PWA on Play Store; performance optimized |
| 8 | Testing, Security Audit & Launch | 31–34 | — | Platform live nationally; all staff trained |
| Post-Launch | Hypercare & Stabilization | 35–44 | — | Zero P1 bugs; first monthly report generated |
| Growth | Enhancements & Expansion | 45–52 | — | WhatsApp, USSD, multi-currency live |

## Sprint Calendar

| Sprint | Weeks | Theme | Deliverable |
| --- | --- | --- | --- |
| Sprint 1 | 1–2 | AWS + DevOps Foundation | Infrastructure running; CI/CD pipeline deploying |
| Sprint 2 | 3 | DB Schema + Auth | Authentication API with MFA; full schema deployed |
| Sprint 3 | 4–5 | Public Website | Full website live in 3 languages |
| Sprint 4 | 6–7 | Member Management | Registration, profiles, digital ID card |
| Sprint 5 | 8 | Mosques + Prayer Times | Mosque management; prayer times public API |
| Sprint 6 | 9–10 | Payments + Marriage Service | MoMo/BK/Visa live; marriage workflow complete |
| Sprint 7 | 11–12 | Remaining 6 Services | Funeral, conduct, hijra, scholarship, tender, jobs |
| Sprint 8 | 13–14 | Payment Hardening | Production payments; SMS/email notifications for services |
| Sprint 9 | 15–16 | Donations + Zakat | Campaigns, Zakat calculator, orphan, Quran programs |
| Sprint 10 | 17–18 | Financial Management | Income/expense, funds, reports, audit log |
| Sprint 11 | 19–21 | Events + Communications | Events, SMS, email, push, internal notifications |
| Sprint 12 | 22–23 | Analytics + Reports | Dashboards, report scheduler, search |
| Sprint 13 | 24–26 | AI Assistant | RAG chatbot, knowledge base, admin UI, moderation |
| Sprint 14 | 27–28 | PWA + Mobile | Service worker, TWA, Play Store submission |
| Sprint 15 | 29–30 | Schools + Performance | School module, caching, accessibility, optimization |
| — | 31 | Regression + Security | Full regression; penetration test; DPP compliance |
| — | 32 | Performance + UAT | Load testing; user acceptance testing; sign-off |
| — | 33 | Training | SuperAdmin, Admin, Operator, Imam training sessions |
| — | 34 | Go-Live | Pilot → Soft Launch → National Launch |

# IMPLEMENTATION RISK REGISTER

| ID | Risk | Phase | Prob | Impact | Mitigation |
| --- | --- | --- | --- | --- | --- |
| R01 | Domain/DNS delays block staging access | 1 | M | M | Start DNS on Day 1; use IP-based access initially |
| R02 | DB schema changes needed after Phase 2 due to missed requirements | 2 | H | H | BA and Tech Lead review schema in Week 1; use migrations strictly |
| R03 | MTN MoMo production credentials delayed | 3 | H | VH | Begin MTN agreement process in Week 1 (procurement lead time ~4 weeks) |
| R04 | BK Online integration more complex than documented | 3 | M | H | Allocate buffer sprint; start BK sandbox in parallel with MoMo |
| R05 | Scope creep from RMC stakeholders during development | All | H | H | Formal change control process; any new feature goes to backlog; PM gates |
| R06 | Key developer unavailability | All | M | H | Code documentation enforced; pair programming; no single-developer modules |
| R07 | Claude API costs exceed budget during AI development | 6 | M | M | Usage monitoring from Day 1; caching identical queries; rate limiting enforced |
| R08 | Play Store review rejection | 7 | M | M | Review Play Store policies pre-submission; prepare policy-compliant description |
| R09 | UAT stakeholders unavailable for testing week | 8 | M | H | Schedule UAT 4 weeks in advance; backup UAT testers identified |
| R10 | Security penetration test reveals critical vulnerabilities | 8 | M | VH | Conduct internal OWASP ZAP scan in Week 28; fix early; pen test confirms |
| R11 | Low adoption post-launch | Post | H | H | Mosque champion program; WhatsApp campaign; leadership endorsement |
| R12 | AI hallucination on Islamic content damages RMC reputation | 6+ | M | VH | Islamic scholar review of knowledge base; strict RAG-only responses; moderation |

## Change Control Process

Any request to add or significantly change a feature during implementation must follow this process:

- Requester submits Change Request (CR) form to PM with: description, business justification, requested timeline

- PM assesses impact on scope, timeline, and team capacity within 3 business days

- Tech Lead assesses technical complexity and effort

- If CR adds > 3 story points: it goes to the product backlog for a future sprint; current sprint is protected

- PM presents significant CRs to RMC leadership with options: defer, remove another feature, or extend timeline

- Approved CRs are added to JIRA with CR reference number; rejected CRs are documented with reason

# COMMUNICATION PLAN

| Communication | Frequency | Format | Audience | Owner |
| --- | --- | --- | --- | --- |
| Daily Standup | Daily (15 min, 09:00) | Virtual call / in-person | Full dev team | PM / Scrum Master |
| Weekly Status Report | Every Friday | Email report (1 page) | RMC Leadership + Tech Lead | PM |
| Sprint Review / Demo | End of every sprint | Live demo on staging | RMC Leadership + BA + Tech Lead | PM + Team |
| Sprint Retrospective | End of every sprint | Team-only meeting | Dev Team | PM / Scrum Master |
| Phase Gate Meeting | End of every phase | Formal presentation | RMC Leadership + All stakeholders | PM |
| Risk Review | Weekly | PM reviews risk register; escalates if needed | PM + Tech Lead | PM |
| Technical Architecture Review | Monthly | Tech discussion meeting | Tech Lead + Backend + DB Eng | Tech Lead |
| Stakeholder Steering Committee | Monthly | Formal meeting + report | RMC Board (if applicable) + Leadership | PM |
| UAT Communication | Pre-UAT (2 weeks notice) | Email + calendar invite | UAT participants | PM + BA |
| Go-Live Announcement | Pre-launch (1 week) | WhatsApp + email + mosque announcement | RMC community | PM + RMC Comms |

## JIRA Project Structure

| Level | Name | Examples |
| --- | --- | --- |
| Epic | Major functional domain | EPIC-01: Authentication, EPIC-02: Member Management, EPIC-08: Payments |
| Story | User-facing feature | As a member, I can register online and verify my phone number via OTP |
| Task | Technical implementation step | Create UsersService.register() method with DTO validation |
| Bug | Defect found in testing | Marriage application form: national ID field accepts non-numeric characters |
| Sub-task | Component of a story | - Write unit tests for registration service - Create Swagger documentation for endpoint |

## Definition of Phase Completion

| Phase Completion Requires | Detail |
| --- | --- |
| Quality Gate — all checks passed | Every item in the phase Quality Gate table must be checked as PASS |
| BA Sign-off | Business Analyst confirms all functional requirements for the phase are met |
| Deployment to staging confirmed | All phase deliverables deployed to staging and verified functional |
| Zero open P1/P2 bugs | No critical or high-severity bugs remain open at phase end |
| Documentation updated | API docs, architecture docs, and test results updated for all phase features |
| Sprint retrospective completed | Team retrospective conducted; action items logged and assigned |
| Phase demo delivered | Live demo given to RMC leadership; feedback documented |
| PM sign-off email sent | PM sends formal phase completion notification to all stakeholders |

— End of Implementation Plan —

Rwanda Muslim Community Digital Platform  |  Implementation Plan v1.0  |  Confidential