RWANDA MUSLIM COMMUNITY

Digital Platform

PHASE 1 — ENVIRONMENT & FOUNDATION SETUP

PARTIAL IMPLEMENTATION PLAN

Pre-AWS Access — Tasks Executable Without Cloud Infrastructure

| Document Attribute | Detail |
| --- | --- |
| Project Name | Rwanda Muslim Community (RMC) Digital Platform |
| Document Type | Phase 1 — Partial Implementation Plan (Pre-AWS) |
| Phase Status | ⚠ PARTIAL — AWS Access Pending |
| Planned Duration | Weeks 1–3 (6 working days/week) |
| Prepared By | Project Management Office |
| Version | 1.0 — June 2026 |
| Status | Active — Partial Execution |
| Methodology | Agile / Scrum with Fixed-Phase Gates |
| Stack | NestJS · Next.js · PostgreSQL · AWS · Docker |

# 1.  CONTEXT & SCOPE OF THIS DOCUMENT

Phase 1 of the RMC Digital Platform covers the complete Environment & Foundation Setup — from AWS cloud infrastructure provisioning through to a working authentication system with role-based access control. The full Phase 1 plan spans Weeks 1–3 and involves 10 infrastructure stories and 12 database/auth stories across two sprints.

This document is a PARTIAL implementation plan. It captures only the work that can proceed immediately — without requiring AWS account access — while AWS provisioning is pending approval. It is designed to be activated the moment the team is assembled, ensuring zero idle time.

⚠ AWS ACCESS CONSTRAINT The RMC AWS account has not yet been provisioned or handed over to the DevOps Engineer. All AWS-dependent tasks (EC2, RDS, VPC, S3, Route 53, ACM, CloudWatch) are blocked until access is granted. This plan identifies every task that can run in parallel on local infrastructure and returns a clear BLOCKED list that the PM must unblock with the client as the highest-priority action item. Estimated unblock deadline target: End of Week 1, Day 3 (to avoid delaying Sprint 2 DB & Auth work).

## 1.1  What This Plan Covers vs. Does Not Cover

| ✅ IN SCOPE — Can Start Immediately | 🔴 OUT OF SCOPE — Blocked on AWS |
| --- | --- |
| Git repository setup & GitFlow branching | AWS VPC, subnets, internet/NAT gateway |
| Docker Compose local dev environment | EC2 instance provisioning (App, DB, Redis servers) |
| Local PostgreSQL database setup (dev/test) | RDS PostgreSQL on AWS (production DB) |
| PostgreSQL full schema design & migrations | AWS S3 bucket creation & configuration |
| NestJS Auth module (register/login/JWT/MFA/RBAC) | Nginx reverse proxy on AWS app server |
| Next.js frontend scaffold with i18n & RTL | SSL/TLS via ACM + Certbot on AWS |
| JIRA project board setup & sprint planning | CI/CD pipeline deploy-to-staging (GitHub Actions) |
| CI/CD pipeline: lint → test → build → scan stages | Prometheus + Grafana + Loki monitoring stack |
| Architecture Decision Record (ADR) document | CloudWatch alarms & Sentry production setup |
| Team NDAs, onboarding, access provisioning | Redis on AWS with production AUTH config |
| Unit tests for all auth stories (≥ 80% coverage) | Staging deployment & end-to-end integration tests |

# 2.  TEAM & RESPONSIBILITIES

| Role | Count | Phase 1 Focus (Partial) | Available Now? |
| --- | --- | --- | --- |
| Project Manager | 1 | Kick-off, JIRA setup, AWS escalation, stakeholder comms | ✅ Yes |
| Tech Lead / Architect | 1 | ADR, DB schema design review, auth module review, Git standards | ✅ Yes |
| DevOps Engineer | 1 | Docker Compose, CI/CD lint/test/build stages (no deploy-to-staging yet) | ✅ Partial |
| Database Engineer | 1 | Full PostgreSQL schema design, local DB setup, migrations, backup plan | ✅ Yes |
| Backend Developer ×2 | 2 | NestJS auth module: register, login, JWT, refresh, MFA, RBAC guards, unit tests | ✅ Yes |
| Frontend Developer (1 of 2) | 1 | Next.js scaffold, Tailwind, i18n (next-intl), Arabic RTL, placeholder pages | ✅ Yes |
| Business Analyst | 1 | Requirements sign-off, acceptance criteria for auth stories, schema review | ✅ Yes |
| QA Engineer | 1 | Test strategy document, unit test review, auth test cases — no staging deploy yet | ⚠ Partial |

# 3.  PRE-CONDITIONS STATUS

The following table maps each original Phase 1 pre-condition to its current status. The PM is responsible for resolving all BLOCKED items before Sprint 1 ends.

| Pre-Condition | Status | Owner | Action Required |
| --- | --- | --- | --- |
| Technical stack approved (NestJS/Next.js/PostgreSQL/AWS) | ✅ READY | PM / RMC | None — approved per plan v1.0 |
| Domain name (rmc.org.rw) registered & DNS access granted | ⏳ IN PROGRESS | PM + RMC IT | Confirm DNS management panel credentials with client this week |
| AWS account created; DevOps has IAM programmatic access | 🔴 BLOCKED | PM → Client | PM to escalate to RMC leadership immediately — highest priority blocker |
| GitHub/GitLab repository created; team access granted | ✅ READY | Tech Lead | Can be done Day 1 — assign to Tech Lead on kick-off |
| JIRA (or equivalent) project board configured | ✅ READY | PM | PM to set up epics/stories before kick-off meeting |
| All team members NDAs signed and onboarded | ⏳ IN PROGRESS | PM + HR | Track NDA completion by end of Day 2; block code access until signed |

⚠ PM ACTION — AWS UNBLOCK Send formal escalation to RMC leadership within 24 hours of project kick-off requesting: 1. AWS account root access or IAM admin credentials for DevOps Engineer 2. Confirmation of preferred AWS region (recommended: af-south-1 Cape Town or eu-west-1 Ireland for latency) 3. Billing/payment method attached to account (required before any resources can be provisioned) Target: DevOps Engineer has AWS console access by Day 3 of Week 1.

# 4.  SPRINT 1 — WEEK 1–2: INFRASTRUCTURE & DEVOPS FOUNDATION

## 4.1  Sprint Goal

Establish the complete local development environment and CI/CD pipeline foundation. Every developer should be able to run the full application stack locally within 10 minutes of cloning the repository. All AWS-dependent infrastructure stories are documented and queued, ready to execute the moment AWS access is granted.

## 4.2  Story Execution Plan — Sprint 1

Legend:  ✅ Execute Now   |   🔴 Blocked — AWS Required   |   Amber rows = blocked stories

| Story ID | Description | Owner | Acceptance Criteria / Notes |
| --- | --- | --- | --- |
| INFRA-001 | Provision AWS VPC — public/private subnets, internet gateway, NAT gateway [BLOCKED — Awaiting AWS] | DevOps | BLOCKED — requires AWS console access. Design VPC CIDR blocks (10.0.0.0/16) and document architecture while waiting. |
| INFRA-002 | Launch EC2 instances: App server (t3.large), DB server (t3.medium), Redis (t3.small) [BLOCKED — Awaiting AWS] | DevOps | BLOCKED — requires AWS. Pre-select AMI (Amazon Linux 2023) and document instance sizing rationale in ADR. |
| INFRA-003 | Install PostgreSQL 16 on EC2 DB server; create rmc_db and users [BLOCKED — Awaiting AWS] | DB Engineer | BLOCKED for production DB. Local PostgreSQL 16 setup is IN SCOPE — execute locally now. |
| INFRA-004 | Install Redis 7 on AWS with AUTH password and maxmemory policy [BLOCKED — Awaiting AWS] | DevOps | BLOCKED for AWS Redis. Docker-based Redis 7 in local Compose is IN SCOPE. |
| INFRA-005 | Nginx reverse proxy + SSL via AWS ACM/Certbot [BLOCKED — Awaiting AWS] | DevOps | BLOCKED — requires EC2. Document Nginx config and test locally with self-signed cert. |
| INFRA-009 | Deploy monitoring stack: Prometheus + Grafana + Loki + Promtail [BLOCKED — Awaiting AWS] | DevOps | BLOCKED for staging deploy. Add monitoring containers to local Docker Compose and test dashboards locally. |
| INFRA-010 | Configure AWS S3 bucket: versioning, lifecycle, block public access [BLOCKED — Awaiting AWS] | DevOps | BLOCKED — requires AWS. Document bucket policy, IAM roles, and CORS config. Use local MinIO in Compose for dev. |
| INFRA-006 | Create GitHub repository; configure GitFlow branches (main, develop, feature/*) | Tech Lead | ✅ Execute Day 1. Branches created; protection rules set; PR template committed; CODEOWNERS file defined. |
| INFRA-007 | Build CI/CD pipeline (GitHub Actions): lint → test → build → security scan stages ONLY | DevOps | ✅ Execute (partial). Build lint/test/build/scan jobs. Deploy-to-staging job created but disabled until AWS ready. |
| INFRA-008 | Docker Compose for local dev: backend, frontend, postgres, redis, mailhog, minio | DevOps | ✅ Execute. docker compose up starts full stack. Any developer can run locally in < 10 min. MinIO replaces S3 locally. |

## 4.3  What DevOps Does While Waiting for AWS

The DevOps Engineer is NOT idle during the AWS access delay. The following tasks have full-day capacity:

| # | Task | Output | Why It Matters |
| --- | --- | --- | --- |
| 1 | Author AWS Architecture Design Document | Architecture diagram (draw.io / Lucidchart) | Speeds up provisioning to < 2 hours once access granted |
| 2 | Write all Terraform / CloudFormation IaC scripts (VPC, EC2, RDS, S3) | .tf files committed to infra/ repo folder | Infrastructure-as-code means one command deploys everything once unblocked |
| 3 | Build complete Docker Compose stack (local dev + test) | docker-compose.yml + .env.example | Every developer runs the full stack locally today — no AWS needed |
| 4 | Configure CI/CD pipeline: lint, unit test, build, Trivy scan jobs | .github/workflows/ci.yml | Team gets automated quality gates from Day 1 of code writing |
| 5 | Document Nginx config, SSL setup, Redis AUTH config (ready to apply on EC2) | Markdown docs in /docs/infra/ | Ops runbook ready — no discovery work when AWS is live |
| 6 | Set up local monitoring stack (Prometheus + Grafana + Loki) in Docker Compose | Working local dashboards | Monitoring config validated locally; AWS deploy is a re-target, not a rebuild |

# 5.  SPRINT 2 — WEEK 3: DATABASE SCHEMA & AUTHENTICATION SYSTEM

## 5.1  Sprint Goal

Design and implement the complete PostgreSQL database schema against the local Docker database. Build the full NestJS authentication and RBAC system with passing unit tests at ≥ 80% coverage. This sprint is fully executable without AWS — local PostgreSQL in Docker Compose is the target database.

⚠ SPRINT 2 DEPENDENCY NOTE Sprint 2 database and auth work targets the LOCAL Docker PostgreSQL instance. Migration scripts must be written to be environment-agnostic via DATABASE_URL in .env — so they execute identically on local Docker and on AWS RDS with zero changes. If AWS access is granted during Sprint 1, the DevOps Engineer can simultaneously provision RDS and the team can test migrations against the real staging DB by Sprint 2 end.

## 5.2  Story Execution Plan — Sprint 2

All Sprint 2 stories are executable without AWS. Stories are blocked only if AWS access enables additional integration testing.

| Story ID | Description | Owner | Acceptance Criteria |
| --- | --- | --- | --- |
| DB-001 | Design and implement complete PostgreSQL schema — all Phase 1–8 tables | DB Eng + Tech Lead | All tables created via TypeORM migrations on local Docker DB. FKs enforced. Indexes applied. Reviewed by Tech Lead and BA. |
| DB-002 | Automated daily DB backup to S3; test restore procedure | DevOps | Backup script written and tested locally (export to /backups). AWS S3 target added as environment variable — activates automatically once AWS live. |
| AUTH-001 | Member registration endpoint — validate inputs, hash password (bcrypt), create user record | Backend Dev | POST /api/v1/auth/register → 201 with userId. Duplicate email/phone → 409. Unit tests passing. |
| AUTH-002 | Login endpoint — validate credentials, issue JWT (15 min) + refresh token (7 days) stored in Redis | Backend Dev | POST /api/v1/auth/login → 200 with tokens. Wrong password → 401. Tokens verified. Unit tests passing. |
| AUTH-003 | Refresh token endpoint — validate refresh, issue new access token, rotate refresh token | Backend Dev | POST /api/v1/auth/refresh → 200 new access token. Used token rejected (Redis blacklist). Tests pass. |
| AUTH-004 | Logout — blacklist refresh token in Redis | Backend Dev | POST /api/v1/auth/logout → 200. Subsequent refresh with same token → 401. Tests pass. |
| AUTH-005 | Phone OTP verification — generate OTP, log to console (no SMS yet), verify endpoint | Backend Dev | POST /api/v1/auth/verify-phone — correct OTP → 200, wrong → 400. OTP expires in 5 min. Tests pass. |
| AUTH-006 | Password reset — forgot-password generates signed token, reset-password validates and updates | Backend Dev | Full flow tested. Reset link expires in 15 min. Old password invalid after reset. Email sent via MailHog locally. |
| AUTH-007 | TOTP MFA setup and verification (speakeasy library) | Backend Dev | Admin can setup MFA. TOTP code accepted within 30-second window. Tested on Google Authenticator + Authy. |
| RBAC-001 | RBAC guards — @Roles() decorator, JwtAuthGuard, RolesGuard on all routes | Tech Lead | Operator cannot access Admin endpoints → 403. SuperAdmin accesses all → 200. 4-tier hierarchy enforced. |
| FE-001 | Next.js scaffold — Tailwind CSS, next-intl i18n, Arabic RTL, font loading, placeholder pages | Frontend Dev | Language toggle switches Kinyarwanda / English / Arabic. RTL layout correct in Arabic. Deployed locally. |

# 6.  DELIVERABLES — PARTIAL PHASE 1

| # | Deliverable | Format | Owner | Status |
| --- | --- | --- | --- | --- |
| 1 | GitHub repo with GitFlow branches, PR template, CODEOWNERS | GitHub repository | Tech Lead | ✅ In Scope |
| 2 | Docker Compose local dev environment (backend/frontend/postgres/redis/mailhog/minio) | docker-compose.yml + .env.example | DevOps | ✅ In Scope |
| 3 | CI/CD pipeline: lint → test → build → scan (deploy stage disabled pending AWS) | GitHub Actions YAML | DevOps | ✅ In Scope |
| 4 | PostgreSQL complete schema — all Phase 1–8 tables with TypeORM migrations | SQL migration files | DB Engineer | ✅ In Scope |
| 5 | Authentication API: register, login, refresh, logout, OTP, password reset, MFA, RBAC | NestJS module (local only) | Backend Dev | ✅ In Scope |
| 6 | Next.js scaffold with multilingual (KY/EN/AR) and RTL support — local only | Next.js project | Frontend Dev | ✅ In Scope |
| 7 | AWS Architecture Design Document (VPC, EC2, RDS, S3 — ready to provision) | Draw.io + Markdown | DevOps + Tech Lead | ✅ In Scope |
| 8 | Terraform / CloudFormation IaC scripts for full AWS infrastructure | .tf files in /infra repo | DevOps | ✅ In Scope |
| 9 | Architecture Decision Record (ADR) document | Markdown in /docs/adr/ | Tech Lead | ✅ In Scope |
| 10 | Unit test suite for all auth endpoints (≥ 80% coverage) | Jest test files | Backend Dev | ✅ In Scope |
| 11 | Swagger / OpenAPI documentation for all auth endpoints | OpenAPI spec at /api/docs | Backend Dev | ✅ In Scope |
| 12 | AWS infrastructure fully provisioned (EC2, RDS, S3, VPC, Redis, monitoring) | Live AWS console | DevOps | 🔴 BLOCKED |
| 13 | Auth API deployed to staging environment | Running on EC2 staging | DevOps | 🔴 BLOCKED |
| 14 | Grafana dashboards operational on staging monitoring server | Live Grafana at monitoring URL | DevOps | 🔴 BLOCKED |

# 7.  PARTIAL PHASE 1 — QUALITY GATE

The following gate applies to Phase 1 partial completion (pre-AWS). The full Phase 1 quality gate (from the master plan) is appended below as reference and activates once AWS access is granted.

## 7.1  Partial Phase 1 Exit Criteria (Pre-AWS)

| Check | Pass Condition | Verifier |
| --- | --- | --- |
| Git Repository | GitFlow branches exist; protection rules active; PR template committed | Tech Lead |
| Docker Compose | docker compose up starts full local stack. Any dev runs it in < 10 min on a clean machine | PM verifies with 1 dev |
| CI/CD Pipeline | Push to develop triggers lint → test → build → Trivy scan. All stages green. Deploy stage present but gated | DevOps |
| Database Schema | All migrations apply cleanly on local Docker PostgreSQL. Rollback tested. Schema reviewed by Tech Lead + BA | DB Engineer + Tech Lead |
| Authentication | All 8 auth endpoints pass unit tests locally. 0 failures. Coverage ≥ 80% on auth module | Backend Dev + QA |
| RBAC | Role hierarchy enforced. Operator → 403 on admin endpoints. SuperAdmin → 200 on all. Unit tests pass | Tech Lead |
| Frontend Scaffold | Language toggle works. Arabic RTL renders correctly. Health-check page returns 200 locally | Frontend Dev |
| Security Scan | npm audit: 0 critical vulnerabilities. Trivy scan on Docker image: 0 critical CVEs | DevOps |
| API Documentation | All auth endpoints documented in Swagger at /api/docs (accessible locally) | Backend Dev |
| AWS Architecture Docs | Architecture diagram and IaC scripts reviewed by Tech Lead; ready to provision on Day 1 of AWS access | DevOps + Tech Lead |
| Team Onboarding | Every team member has signed NDA, has repo access, can run docker compose up successfully | PM |

## 7.2  Full Phase 1 Exit Criteria (Activates When AWS Access Granted)

These checks are from the master implementation plan (v1.0) and become active once AWS infrastructure is provisioned:

| Check | Pass Condition |
| --- | --- |
| Infrastructure Health | All EC2, RDS, Redis instances healthy; no alarms in CloudWatch |
| CI/CD Deploy to Staging | Push to develop auto-deploys to staging within 10 minutes |
| Auth — Integration Tests | All 8 auth endpoints pass integration tests on staging. 0 test failures |
| Monitoring | Grafana shows live metrics on staging; Loki ingesting logs; Sentry connected |
| Database Backup / Restore | S3 backup script runs at 02:00; restore procedure tested and documented |

# 8.  RISKS & MITIGATIONS

| Risk | Prob | Impact | Mitigation |
| --- | --- | --- | --- |
| AWS access delayed beyond Week 1 | HIGH | HIGH | PM escalates to RMC leadership on Day 1. All non-AWS work front-loaded (DB, Auth, Docker, CI/CD). IaC scripts prepared for immediate execution. |
| Domain DNS propagation delays staging URL | MED | MED | Start DNS delegation in Week 1. Use IP-based access initially. Use staging.rmc.org.rw subdomain once DNS propagates. |
| DB schema requires major revision after Phase 2 | MED | HIGH | BA + Tech Lead conduct schema review workshop in Week 1. Treat schema as living document; all changes via TypeORM migrations — never manual SQL. |
| MFA library incompatibility with authenticator apps | LOW | LOW | Use battle-tested speakeasy library. Test with Google Authenticator and Authy on iOS and Android in Sprint 2. |
| Team member unavailable at sprint start | MED | MED | PM confirms availability of all team members before kick-off. NDA delays handled by HR in parallel. Critical-path roles (DevOps, DB Eng, Backend) have no single-developer dependency. |
| Developer machine setup delays (Node, Docker, etc.) | MED | LOW | Publish .env.example, README with exact setup steps, and recorded setup video before kick-off. Target: every dev running locally within 30 minutes of first clone. |

# 9.  PM ACTION PLAN — WEEK 1 PRIORITY TASKS

The following actions must be completed by the Project Manager in the first 3 working days to unblock the team and protect the Phase 1 timeline:

| # | Action | Deadline | Owner | Priority |
| --- | --- | --- | --- | --- |
| 1 | Send formal written escalation to RMC leadership requesting AWS account access — include IAM requirements doc | Day 1 — AM | PM | 🔴 CRITICAL |
| 2 | Conduct project kick-off meeting — distribute roles, explain partial plan, confirm team availability | Day 1 — PM | PM | 🔴 CRITICAL |
| 3 | Set up JIRA project: import all Phase 1 epics and stories; assign Sprint 1 stories to team | Day 1 — PM | PM | ⚠ HIGH |
| 4 | Track NDA completion for all team members; block repo access until signed | Day 2 EOD | PM + HR | ⚠ HIGH |
| 5 | Confirm domain registrar DNS management access with RMC IT — initiate delegation if not done | Day 2 EOD | PM + RMC IT | ⚠ HIGH |
| 6 | Schedule BA + Tech Lead + DB Engineer schema workshop — target: schema frozen by end of Week 1 | Day 2 | PM | ⚠ HIGH |
| 7 | Distribute this partial plan to all team members; confirm understanding of what is IN SCOPE vs BLOCKED | Day 1 — PM | PM | ℹ STANDARD |
| 8 | Set up weekly status report template; send first report to RMC leadership at end of Week 1 | End of Week 1 | PM | ℹ STANDARD |

# 10.  STAKEHOLDER TOUCHPOINTS — PHASE 1 (PARTIAL)

| Meeting / Communication | Timing | Audience | Purpose |
| --- | --- | --- | --- |
| Project Kick-off Meeting | Day 1 | Full team + RMC leadership | Align on scope, partial plan, AWS blocker, team roles, sprint schedule |
| AWS Escalation Meeting | Day 1–2 | PM + RMC IT/Leadership | Present AWS requirements doc; get commitment on access timeline |
| Schema Review Workshop | End of Week 1 | Tech Lead + BA + DB Engineer | Finalise and freeze full database schema before coding begins |
| Daily Standup (15 min) | Daily 09:00 | Full dev team | Progress, blockers, dependency flags — especially AWS access status |
| Week 1 Status Report | End of Week 1 | RMC Leadership | Progress summary; AWS blocker status; team setup confirmation |
| Sprint 1 Review / Demo | End of Week 2 | RMC Leadership + BA | Demo: Docker Compose running, CI/CD pipeline green, DB schema walkthrough |
| Sprint 2 Review / Demo | End of Week 3 | RMC Leadership + BA | Demo: Auth API working locally; RBAC tested; multilingual frontend live |
| Phase 1 Gate Meeting | After AWS live + deploy | All stakeholders | Present full Phase 1 quality gate results; get sign-off before Phase 2 starts |

# 11.  TRANSITION: PARTIAL → FULL PHASE 1

Once AWS access is granted, the following actions activate immediately. These are already prepared and require no additional planning — only execution:

| # | Task | Estimated Effort | Owner | Unlocks |
| --- | --- | --- | --- | --- |
| 1 | Run Terraform / CloudFormation scripts to provision full AWS environment | ~4–6 hours | DevOps | All INFRA-001 through INFRA-005, INFRA-010 stories |
| 2 | Configure Nginx + SSL/ACM on EC2 app server | ~2 hours | DevOps | INFRA-005; staging URL accessible |
| 3 | Enable CI/CD deploy-to-staging job in GitHub Actions | ~1 hour | DevOps | INFRA-007; auto-deploy on merge to develop |
| 4 | Run DB migrations on AWS RDS; verify same as local result | ~1 hour | DB Engineer | DB-001 staging validation; integration test target |
| 5 | Configure S3 backup job target from local script to real S3 bucket | ~1 hour | DevOps | DB-002; backup-to-S3 active |
| 6 | Deploy monitoring stack (Prometheus + Grafana + Loki) to staging EC2 | ~3 hours | DevOps | INFRA-009; Grafana dashboards live |
| 7 | Deploy Auth API to staging; run integration test suite against staging | ~2 hours | Backend Dev + QA | Full Phase 1 quality gate; Phase 1 complete |

⚠ TOTAL ESTIMATED TIME TO FULL PHASE 1 COMPLETION AFTER AWS ACCESS If all local work (DB schema, auth module, Docker Compose, CI/CD, frontend scaffold) is complete as planned, the remaining AWS-dependent tasks (Terraform, Nginx, deploy, monitoring) require approximately 1–2 working days. Full Phase 1 completion is achievable within 1 sprint cycle after AWS access is granted.

— End of Phase 1 Partial Implementation Plan —

Rwanda Muslim Community Digital Platform  |  Implementation Plan v1.0 (Phase 1 Partial)  |  Confidential  |  June 2026